## Internal Resource Cost Estimate
Project Stage | Analysis and Design |  | Build |  |  |  | Test |  |  | Training & Rollout
Roles | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | FTE Effort - Annual | Annual Salary Estimate ($) | Cost estimate ($)
Subject Matter Experts (SME) - Finance | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 100000 | 50000
Subject Matter Experts (SME) - Manufacturing | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 100000 | 30000
Subject Matter Experts (SME) - Supply Chain | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  |  | 0.25 | 100000 | 25000
Subject Matter Experts (SME) - Sales and Marketing |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  |  | 0.2 | 100000 | 20000
Subject Matter Experts (SME) - Warehouse and Inventory |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 |  |  | 0.2 | 100000 | 20000
Subject Matter Experts (SME) - Point of Sale - Retail |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.25 | 100000 | 25000
Technical - System Admin - User security, technical support |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.13333 | 100000 | 13333.3333
Technical - Reports development and BI | Test Jul: 0.8; Test Aug: 0.8; Test Sep: 0.8; Training & Rollout Oct: 0.8; Training & Rollout Nov: 0.8 | 0.33333 | 100000 | 33333.3333
Tehnical - Outputs development - Invoice, PO output forms | Test Jul: 0.5; Test Aug: 0.5; Test Sep: 0.5; Training & Rollout Oct: 0.5; Training & Rollout Nov: 0.5 | 0.20833 | 100000 | 20833.3333
Technical - ERP customisations |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.375 | 100000 | 37500
Technical - ERP Integrations |  |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.2 | 0.2 | 0.2 |  | 0.38333 | 100000 | 38333.3333
Business Analyst | [12 empty] | 1 | 100000 | 100000 | bar: Analysis and Design Jan to Training & Rollout Dec
Project Manager | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 100000 | 80000
Test Manager | Build Apr: 0.5; Build May: 0.5; Build Jun: 0.5; Test Jul: 0.5; Test Aug: 0.5; Test Sep: 0.5 | 0.25 | 100000 | 25000
Change Manager | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 100000 | 30000
Total Cost Estimate - Internal Resources for the project | [14 empty] | 548333.3333